## Summary
#VALUE!
Summary of Projects
Date: | 2026-02-05
| Project Count | Contract Amount | Gross Amnt TD Invoiced | Aged Receivables | Received | Contract Backlog
Commercial
Active | 15 | 21709121.98 | 14872621.71 | 1279679.45 | 13580239.98 | 6836500.27
Completed * | 16 | 7078105.8 | 7012831.25 | 0 | 7012831.25 | 65274.55
| Sub Total: | 28787227.78 | 21885452.96 | 1279679.45 | 20593071.23 | 6901774.82
Residential
Active | 13 | 316891.98 | 168293.64 | 39773.59 | 128520.05 | 148598.34
Completed * | 48 | 1284794.6 | 1284228.17 | 66569.76 | 1217658.41 | 566.43
| Sub Total: | 1601686.58 | 1452521.81 | 106343.35 | 1346178.46 | 149164.77
Repairs
Active | 1 | 12000 | 12000 | 0 | 12000 | 0
Completed* | 47 | 241356.67 | 230921.67 | 4625 | 228796.67 | 10435
| Sub Total: | 253356.67 | 242921.67 | 4625 | 240796.67 | 10435
Maintenance
Active | 0 | 0 | 0 | 0 | 0 | 0
Completed* | 34 | 199047.5 | 142197.5 | 42995.5 | 108202 | 56850
| Sub Total: | 199047.5 | 142197.5 | 42995.5 | 108202 | 56850
Grand Totals: | Active | 22038013.96 | 15052915.35 | 1319453.04 | 13720760.03 | 6985098.61
| Completed | 8803304.57 | 8670178.59 | 114190.26 | 8567488.33 | 133125.98

## Commercial
Commercial Projects
| Date: | 2026-02-05
Active Commercial Projects
|  | Commercial Projects | [7 empty] | Date: | 2026-02-05
Active Commercial Projects
| Job Name | Type of Work | Supervisor | Salesperson | Project Status | Contract Signed | Contract Amount | Invoiced to Date | Received to Date | Aged Receivables | % of Contract Invoiced | Backlog | Notes | NTO |  | Project Status
| Leisure Beach S. Condo 2900 Banyan St., Ft. Lauderdale, Fl 33316 | SPF | AJ | Shawn | In Process | Yes | 135500 | 151228.44 | 118031.1 | 33197.34 | 111.6% | -15728.44 | Inv no 43811 - $30,448.00 - Temp Roofing - emailed on 10/28/25, inv no 43869 - Permit Fees - $2749.34 - emailed on 11/26/25 | YES
| Palm Beach Yacht Center 7848 S. Federal Hwy., Lantana, Fl 33462 | SPF | Scott | Scott | In Process | Yes | 282237 | 84671.1 | 84671.1 | 0 | 30% | 197565.9 | Not started | YES
| Geraldo Abreu - Deer Run 2 4301 Coral Springs Drive Coral Springs, FL 33065 | Tile | AJ | Santiago | In Process | Yes | 174382.54 | 8719.13 | 8719.13 | 0 | 5% | 165663.41 | Not started | YES
| Lime Bay Condominium 9190 Lime Bay Blvd Tamarac, FL 33321 | SPF | AJ | Scott | In Process | Yes | 1479799 | 570755.1 | 434380.3 | 136374.8 | 38.57% | 909043.9 | Inv no 43941- $136,374.80 - Pay App no 5 - 40% of Commencement - BUILDING 15 - 9401 Lime Bay Blvd / C/O # 3: 1 ea. AC Repairs and Line Jack Install. | YES |  | Not Started
| Brian Tansey / Worth Avenue Yachts 866 NE 20th Avenue Ft. Lauderdale, Fl 33304-3223 | SPF/Flat | AJ | Santiago | Completed | Yes | 41372.5 | 41372.5 |  | 0 | 100% | 0 |  | Yes |  | Completed
| Protech E2 103375 Oversees Hwy, Key Largo, FL 33037 | Foam | AJ | Scott | Completed | Yes | 34752 | 34752 |  | 0 | 100% | 0 |  | YES |  | Delayed
| Alpine Woods Condo 9600 Griffin Road, Cooper City, FL 33328 | SPF | AJ | Scott | In Process | Yes | 1379892.75 | 1511347.97 | 1298987.6 | 199658.09 | 109.5% | -131455.22 | REPAIRS - $2,197.25- (Inv no 43514-$570.00- sent 6/25/25, , Inv no 43645 - $477.25 - sent 8/25/25, Inv no 43646 - $575.00 - sent 8/25/25, Inv no 43647 - $575.00 - sent 8/25/25), COMMERCIAL - $197,460.84 - (Inv no 43886 - $130,545.00 - Wood bill (bill may be reduced by 50% as per Scott) - presently on hold as per Scott to meet w/ Alpine Wood), Inv no 43945 - $66,915.84 - Pay App no 36 - emailed on 1/6/26 | YES | MIsc reve. $178797.47 -
| Admiral Towers 1020 Meridian Avenue Miami Beach, Fl 33139 | SPF | AJ | Shawn | In Process | Yes | 439157.47 | 513937.13 | 383848.42 | 130088.71 | 117% | -74779.66 | TEMP ROOFING - $28,217.22 - (Inv no 43833 - $28,217.22 emailed on 11/11/25),COMMERCIAL - $101,871.49 ( Inv no 43891 - $101,871.49 - 20% due upon 50% Completion and Final 50% Billing for Change Order no 2 & 3 - emailed on 12/11/25) | YES
| Regal Trace Ltd 540 NW 4th Ave, Fort Lauderdale, FL 33311 | Shingle | AJ | Scott | Completed | Yes | 1945117.73 | 1852763.26 |  | 0 | 95.25% | 92354.47 |  | NO |  |  | Regal Trace Ltd 540 NW 4th Ave Fort Lauderdale, FL 33111 954-468-1800
| Holy Acres Pet Resort | Foam | AJ | Scott | Completed | Yes | 25000 | 25000 |  |  | 100% | 0 |  | NO |  | Litigation
| Westview Condominium 3 9142 Limetree Ln, Pembroke Pines FL 33024 | Modified | AJ | Shawn | In Process | Yes | 639307.8 | 400443.4 | 400443.4 | 0 | 62.64% | 238864.4 |  | Yes |  | Pending
| High Point Court Ass., Inc. 211 High Point Blvd, Boynton Beach, FL 33445 | Shingle | Blake | Shawn | In Process | Yes | 608732.7 | 645337.48 | 542930.6 | 102406.88 | 106% | -36604.78 | Inv no 43878 - $51,917.00 - Pay app no 7 -emailed on 12/8/25 , Inv no 43955 - $50,489.88 - Pay app no 9 -emailed on 1/6/26 s/b billed in full per Scott | YES
| Lakeside Village 500 Lori Drive Palm Springs, Fl 33461 | Shingle | Blake | Shawn | In Process | Yes | 7849873.54 | 5116010.83 | 4780664.53 | 335346.3 | 65.17% | 2733862.71 | EXTRA WORK - Inv no. 43626 - $9,834.62 - Repairs performed due to roof leak caused by The Cool Team (A/C contractor) - Client: Adriana Dilworth, COMMERCIAL - Inv no 43940 - $325,511.68 | YES
| Island Crest Condominium 10680 S. Ocean Drive Jensen Beach, Fl 34957 | SPF | Blake | David | In Process | Yes | 568634 | 596906.11 | 526787.6 | 70118.51 | 105% | -28272.11 | COMMERCIAL - $70,118.51 - Inv no 43809- $22,500.00 - Temp Roofing - emailed 10/28/25 - Update Amount of Invoice to $22,500.00 as per SCI Agreement and Inv no 43936 - Final Bill - not paid yet but have copy of check for payment | YES
| High Point of Delray 292 High Point Blvd, Delray Beach, FL 33445 | Shingle Peel & Stick | Blake | Shawn | In Process | Yes | 2113635.68 | 2132834.68 | 2113634.68 | 19200 | 100.9% | -19199 | Inv no 43892 - $19,200.00 - Wood Bill - Pay App no 11:s/b another approx. $50k for addl woodwork | YES
| KAPS-ALL Packaging Systems 251 N Congress Avenue, Delray Beach, Fl 33445 | SPF | Blake | Shawn | In Process | Yes | 181000 | 36200 | 36200 | 0 | 20% | 144800 |  | YES
| The Land of President 2500-3050 Presidential Way, West Palm Beach | SPF | Blake | Shawn | In Process | Yes | 457084 | 22854.2 | 22854.2 | 0 | 5% | 434229.8 |  | YES
| Mark One Condominium 1050 SE 15th Street Ft. Lauderdale, Fl 33316 | SPF/Flat | AJ | Garry | Completed | Yes | 109450 | 109450 |  |  | 100% | 0 |  | YES
| Lauderdale West | Tile | Shawn | Scott | In Process | Yes | 2362972.5 | 1672943.6 | 1641437.3 | 31506.3 | 70.8% | 690028.9 | Wood Bills: $2,000.00 | NO |  |  | Lauderdale West
| Greensward Village | Shingle | David | EJ | Completed | Yes | 1590731 | 1617810.92 |  | 0 | 101.7% | -27079.92 |  | NO |  | No Contract | Greensward Village 745 Greenward Ct. Delray Beach, FL 33069 954-984-1000
| Isles of Boca Association 23229 Fountain View Drive Boca Raton, Fl 33433 | Tile | Blake | Shawn | Litigation | Yes | 3036913 | 1408432.54 | 1186650.02 | 221782.52 | 46.38% | 1628480.46 | 14 - $115,670.72 - sent on 3/21/25, 15 - $105,703.32 - originally emailed on 3/28/25 - revised sent on 4/25/25, 16 - on Hold, Fees - inv no 43327- $408.50 - 4/9/25 | YES
| Mariner's Way Condo 2707 14th Street Causeway Pompano Beach, Fl 33062 | SPF | AJ | Shawn | Completed | Yes | 89533.47 | 89533.47 |  |  | 100% | 0 |  | YES |  | In Process
| Amkin Mgmt-Bainbridge | Recoat / SPF | Scott | Scott | Completed | Yes | 1100000 | 1100000 |  |  | 100% | 0 |  | NO |  | STATUS LEGEND: | Amkin Mgmt-Bainbridge 1501 Colquitt Bainbridge, GA
| Amkin Mgmt-Flamingo Seafood | TPO | AJ | Scott | Completed | Yes | 26880 | 26880 |  |  | 100% | 0 |  | NO |  | In Process | Amkin Mgmt-Flamingo Seafood 2798 E Atlantic Blvd. Pompano Beach, FL 32062
| Amkin Mgmt-Westbay | Recoat | Scott | Scott | Completed | Yes | 74380 | 74380 |  |  | 100% | 0 |  | NO |  | POSTPONED | Amkin Mgmt-Westbay 311 W Bay Street Jacksonville, FL 32202
| Meadowbrook Tower L | SPF | Shawn | Shawn | Completed | Yes | 206716.13 | 206716.13 |  |  | 100% | 0 |  |  |  |  | Meadowbrook Tower L 319 NE 14 Avenue Hallandale, FL 33009 416-453-7996
| Casa Blanca Condominiums 701 NE 1st Court Hallandale, Fl 33009 | SPF | AJ | Shawn | Completed | Yes | 315441.97 | 315441.97 |  |  | 100% | 0 |  | YES
| Winston Towers 400 | SPF | Shawn | Shawn | Completed | Yes | 1106726 | 1106726 |  |  | 100% | 0 |  |  |  |  | Donnil Kenney 3095 S Military Trail Lake Worth, FL 33463 561-644-0077
| Donnil Kenney | SPF | Garry | Scott | Completed | Yes | 170825 | 170825 |  |  | 100% | 0
| The Field - British Oak | Shingle & Flat | Garry | Garry | Completed | Yes | 97150 | 97150 |  |  | 100% | 0 |  |  |  |  | The Field - British Oak 3281 Griffin Road Fort Lauderdale, Florida 33312 954-649-6082 Marie McMullen
| Regency Island Dunes | SPF N. Bldg Porta Cochere Metal - S. Bldg | David | David | Completed | Yes | 144030 | 144030 |  |  | 100% | 0 |  |  |  |  | Regency Island Dunes 8640/8650 S Ocean Dr Jensen Beach, FL 34957
[6 empty] | Totals | 28787227.78 | 21885452.96 | 13580239.98 | 1057896.93 |  | 6901774.82
| Commercial Projects | Project Count | Contract Amount | Gross Amnt TD Invoiced | Outstanding Invoice Amnt | Gross Amnt Paid | Contract Amnt Not Invoiced
| Projects In Process: | 14 | 18672208.98 | 13464189.17 | 1057896.93 | #REF! | 5208019.81
| Projects Delayed: | 0 | 0 | 0 | 0 | #REF! | 0
| Projects In Pending: | 0 | 0 | 0 | 0 | #REF! | 0
| Projects with No Contract: | 0 | 0 | 0 | 0 | #REF! | 0
| Projects In Litigation: | 1 | 3036913 | 1408432.54 | 221782.52 | #REF! | 1628480.46
| Sub-Total: | 15 | 21709121.98 | 14872621.71 | 1279679.45 | #REF! | 6836500.27
| Projects In Completed: | 16 | 7078105.8 | 7012831.25 | 0 | #REF! | 65274.55
| Grand Total: | 31 | 28787227.78 | 21885452.96 | 1279679.45 | #REF! | 6901774.82

## Residential
Residential Projects
| Date: | 2026-02-05
Active Residential Projects
| Project Info. |  |  |  | Project Status |  | Project Bookkeeping | [5 empty] | Comments | NTO
[7 empty] | Gross Amnt Invoiced: | 168293.64 | <-Active Projects Amnts-> |  | Gross Outstanding Invoiced Amnt: | 39773.59
| Job Name | Type of Work | Supervisor | Salesperson | Project Status | Contract Signed | Contract Amount | Gross Amnt TD Invoiced | Outstanding Invoice Amnt | Gross Amnt Paid | % of Contract Invoiced | Contract Amnt Not Invoiced |  |  | Project Status
| Darrylle Hood 3549 SW 14th St, Ft Lauderdale, FL 33312 | Shingle | AJ | Shawn | Completed | Yes | 18022.4 | 0 | 0 | 0 | 0% | 18022.4 |  | YES
| Jason Finch 565 Holly Drive, Palm Beach Gardens, Fl 33410 | Shingle | Shawn | Shawn | In Process | Yes | 16403.14 | 16403.14 | 0 | 16403.14 | 100% | 0 | Ygrene Financing Paid
| MAURICE PIETRACULPA Boynton leisureville | SPF ROOF RECOVERING | Repairs | Terry | Pending | Yes | 9000 | 0 | 0 | 0 | 0% | 9000 |  | Louis foam truck scheduled for 1/31/26
| Daniel Poliseo 12399 NW 80th Place, Parkland, Fl 33076 | Foam - Seam Tape | AJ | Santiago | In Process | Yes | 48726.81 | 9745.36 | 0 | 9745.36 | 20% | 38981.45
| Monica Gonzalez Zuniga 5835 TARRAGON DR, WEST PALM BEACH, FL, 33415 | SPF Foam Flat Roof | Blake | Terry | In Process | Yes | 27868.09 | 0 | 0 | 0 | 0% | 27868.09 | Credit Approved by Renew Financial
| Scott Stoik 26201 SW 167 Avenue, Homestead, Fl 33031 | SPF Foam Flat Roof | AJ | Santiago | In Process | Yes | 34334.12 | 34334.12 | 13733.65 | 20600.47 | 100% | 0 | Billed for 20% deposit and 40% upon commenecement Paid in Full, Billed for 40% upon completion on 1/27/2026 not paid yet
| Mike Feingold 9325 SW 16th Rd W, Boca Raton, Fl 33428 | Modified Roof System | Garry | Garry | Completed | Yes | 5000 | 5690.69 | 0 | 5690.69 | 113.8% | -690.69
| G.K. Windows Treatments 231 SW 5th Street, Pompano Beach, Fl 33069 | SPF Roof System | Garry | Garry | Completed | Yes | 90000 | 93670.38 | 39670.38 | 54000 | 104.1% | -3670.38 | Inv no 43950 - $39,670.38 - Final bill and Permit Fees
| David Gross 3864 NW 63rd Terrace Coral Springs, Fl 33067 | Tiles | AJ | Santiago | In Process | Yes | 25174.32 | 5034.86 | 0 | 5034.86 | 20% | 20139.46
| Annisha Armoogan 6420 Oak Street, Hollywood, Fl 33024 | Shingle | AJ | Santiago | Completed | Yes | 11601.45 | 12410.7 | 0 | 12410.7 | 107% | -809.25
| Lou Ann Banks 408 NE 9th Avenue, Ft. Lauderdale. Fl 33301 |  |  | Garry | Completed | Yes | 33900 | 33900 | 0 | 33900 | 100% | 0 | inv no 43885 - Final Bill
| Lynn Silverman 911 NE Sandalwood Place, Jensen Beach, Fl 34957 | Shingle | Blake | Santiago | Completed | Yes | 14435.66 | 14861.04 | 0 | 14861.04 | 102.9% | -425.38
| Joe Simmons 7627 SW 102 Place, Miami, Fl 33173 | SPF | AJ | Scott | Completed | Yes | 23700 | 23700 | 14220 | 9480 | 100% | 0 | Inv no 43928 - $14220.00 - Final Bill
| Jordan Schilt 3725 Piedmont Street Hollywood, Fl 33021 | Tile | AJ | Santiago | In Process | Yes | 18825.5 | 11295.3 | 0 | 11295.3 | 60% | 7530.2 | inv no 43907 - $7,530.20 - 40% Upon Commencement - emailed on 12/17/25- Awaiting payment status from HOA association since Jordan has moved from community and is no longer with the HOA
| Christina Fry 584 SW 131st Ave, Davie, fL 33325 | Shingle | AJ | Santiago | Delayed | Yes | 10085 | 0 | 0 | 0 | 0% | 10085 | On Hold, No Money
| Jim Balistreri 321 SE 15th Avenue Deerfield, Fl 33441 | SPF | AJ | Garry | Completed | Yes | 41000 | 45947.1 | 0 | 45947.1 | 112.1% | -4947.1
| Lauderdale West: James & Virginia Holman 8217 NW 15 Ct. Plantation, Fl 33322 | Tiles | Shawn | Shawn | Completed | Yes | 5850 | 5850 | 0 | 5850 | 100% | 0
| Peter Chesky 1171 Faieview Ln, West Palm Beach | Metal Aluminum | Blake | Santiago | In Process | Yes | 60799.85 | 45119.94 | 24319.94 | 20800 | 74.21% | 15679.91 | Billed for 30% deposit (paid) and 40% upon completion (unpaid) on 01/27/2026
| Jack English Lake Worth Country Club 5279 Fountain Dr. S. Lake Worth, Fl 33467 | Modified Bitumen | Blake | Garry | Completed | Yes | 32675 | 32675 | 0 | 32675 | 100% | 0
| Anthony Santilli 5130 NW 57th Way Coral Springs, Fl 33067 | Tile | AJ | Shawn | In Process | Yes | 35541 | 23150 | 0 | 23150 | 65.14% | 12391
| Charles Graves 531 NE 39th Street, Deerfield Beach, Fl 33064 | Shingles | AJ | Shawn | Completed | Yes | 9938.4 | 9938.4 | 0 | 9938.4 | 100% | 0
| Jennifer & David Hickman D/D Lobster Company Inc. 16032 Prestwich Dr. E, Loxahatchee, FL 33470 | Shingle | Blake | Scott/Blake | Completed | Yes | 13066.07 | 13066.07 | 0 | 13066.07 | 100% | 0
| Carol Cutillo 19631 Delaware Cricle, Boca Raton, Fl 19631 | Shingle | Blake | Joshua | Completed | Yes | 11612.47 | 11612.47 | 0 | 11612.47 | 100% | 0
| Marie J. Leo 6329 Cleveland Street Hollywood, Fl 33024 | SPF Foam Flat Roof | AJ | Santiago | Pending | Yes | 17795.45 | 10872.22 | 1100 | 9772.22 | 61.1% | 6923.23 | 12 Month Payment Plan - 5 of 12 payments - Client made payment 4 of 12) - inv no: 43930- $1,100.00 - emailed 12/23/25, 1/20/26
| Anisha Eckroth 2288 Gabriel Lane West Palm Beach, Fl 33406 | Roof Repair | Blake | Santiago | Pending | Yes | 950 | 950 | 200 | 750 | 100% | 0 | inv no 43700 - $200.00, Payment arrangement for $950.00 @ $200.00 bi-weekly billing until full contract amount is paid full
| Desmond Arscott 4410 NE 3rd Avenue Pompano Beach, Fl 33064 | Shingle | AJ | Garry | Completed | Yes | 9210 | 9210 | 0 | 9210 | 100% | 0
| Clover Williams 3188 La Mirage Drive Lauderhill, Fl 33319 | Tile | AJ | Santiago | Completed | Yes | 25605 | 25605 | 0 | 25605 | 100% | 0 | Warranty and ROL
| Lisa Sawin 637 56th Street West Palm Beach, Fl 33407 | Shingle | Blake | Santiago | Completed | Yes | 8983.65 | 9721.15 | 0 | 9721.15 | 108.2% | -737.5 | Warranty and ROL
| Shelly-Ann M. Knight 8811 Cleary Blvd Plantation, Fl 33324 | Shingles | AJ | Santiago | Completed | Yes | 10237.68 | 10237.68 | 0 | 10237.68 | 100% | 0 | Warranty and ROL
| Eneida Werner 11719 Timbers Way Boca Raton, Fl 33428 | Shingle | Blake | Joshua | Pending | Yes | 11388.7 | 11388.7 | 420 | 10968.7 | 100% | 0 | 5 Month Payment Plan - invoice no 43775 - $210.00 - 4 of 5 - emailed on 10/14/25 - invoice no 43908 - $210.00 - 5 of 5 - emailed on 12/17/25
| Helen Stern 2232 SW 33rd Way Fort Lauderdale, Fl 33312 | SPF Roof System | Shawn | Shawn | Completed | Yes | 28962 | 28962 | 0 | 28962 | 100% | 0
| Lora Delorenzo 816 Blueberry Drive, Wellington, Fl 33414 | Shingle | David | Joshua | Completed | Yes | 22416.4 | 22416.4 | 0 | 22416.4 | 100% | 0
| Marco Lopez-Calleja 2538 Bahia Road, West Palm Beach, Fl 33408 | Shingle | Blake | Garry | Completed | Yes | 16117.47 | 16117.47 | 0 | 16117.47 | 100% | 0 | Warranty and ROL
| Mark Hosang 3375 Sw 2nd Ct. Deerfield Beach, Fl 33442 | Shingle | AJ | Joshua | Completed | Yes | 28102.73 | 28102.74 | 0 | 28102.74 | 100% | -0.01
| Steve Evans 234 Moccasin Trail West, Jupiter, Fl 33458 | Shingle | Blake | Joshua | Completed | Yes | 19764.95 | 19764.95 | 0 | 19764.95 | 100% | 0 | Warranty and ROL
| Steve Serle 5820 N Federal Hwy Boca Raton, Fl 33308 | Tile | AJ | Joshua | Completed | Yes | 4000 | 4000 | 0 | 4000 | 100% | 0 | Warranty and ROL
| Steve Serle 10296 Hidden Springs Ct. Boca Raton, Fl 33498 | Tile | Blake | Joshua | Completed | Yes | 15661 | 15661 | 0 | 15661 | 100% | 0 | Warranty and ROL
| Tommy Smith 5845 Clubhouse Drive, Vero Beach, Fl 32967 | Tile | David | David | Completed | Yes | 68000 | 68000 | 0 | 68000 | 100% | 0
| Mia Krauss 1209 NW 7th St, Boca Raton, Fl 33486 | Shingle | Blake | Joshua | Completed | Yes | 10498.75 | 10498.75 | 0 | 10498.75 | 100% | 0
| Laurie Ellis 5810 NE 18th Avenue Ft. Lauderdale, Fl 33334 | Tile | AJ | Joshua | Completed | Yes | 34084.12 | 34084.12 | 0 | 34084.12 | 100% | 0
| Leroy Collins 3801 Falcon Ridgfe Circle, Weston Fl 33331 | Tile | AJ | Shawn | Completed | Yes | 40200 | 40200 | 0 | 40200 | 100% | 0 |  | No | Not Started
| Michael Salus Const - 208 SE | Standing Seam Metal (Galvalume) | AJ | Shawn | Completed | Yes | 54626 | 54626 | 0 | 54626 | 100% | 0 |  | NO | Pending
| Michael Salus Const - 2506 NE | Standing Seam Metal (Galvalume) | AJ | Shawn | Completed | Yes | 56886 | 56886 | 0 | 56886 | 100% | 0 |  | Yes | Completed
| Monique Chasse 112 NE 4th Avenue Deerfield Beach, Fl 33442 | Shingle | AJ | Joshua | Completed | Yes | 20500 | 20500 | 0 | 20500 | 100% | 0 |  | YES | Delayed
| Michael Salus Const - 900 SE | Standing Seam Metal (Galvalume) | AJ | Shawn | Completed | Yes | 40726 | 40726 | 0 | 40726 | 100% | 0 |  | NO | Litigation
| Doxey Forrester 201 Wrena Drive West Palm Beach, Fl 33409 | Shingle | David | Joshua | Completed | Yes | 27774.2 | 27774.2 | 0 | 27774.2 | 100% | 0 | Ygreene | YES | In Process
| Mimi Goon 1520 NW 96th avenue Plantation, Fl 33322 | Tile | AJ | Shawn | Completed | Yes | 47376 | 52256 | 0 | 52256 | 110.3% | -4880 | Renew Financial | NO | No Contract | Greensward Village 745 Greenward Ct. Delray Beach, FL 33069 954-984-1000
| Jim Zeller 3561 NW 7 Court Lauderhill, Fl 33311 | Shingle/Modified | AJ | Joshua | Completed | Yes | 11372.85 | 11441 | 0 | 11441 | 100.6% | -68.15 |  | YES |  | Isles of Boca Association 23229 Fountain View Drive Boca Raton, Fl 33433
| Michael Salus Const - 701 SE | Standing Seam Metal (Galvalume) | AJ | Shawn | Completed | Yes | 59798 | 59798 | 0 | 59798 | 100% | 0 |  | NO |  | Lauderdale West
| Williams Schwartz | Tile | David | Shawn | Completed | Yes | 80194 | 80194 | 0 | 80194 | 100% | 0 |  | YES
| Richard Knapp | Recoat | Garry | Garry | Completed | Yes | 16500 | 16500 | 0 | 16500 | 100% | 0 |  | YES
| Smith, Randy | Shingle | Shawn | Shawn | Completed | Yes | 15380.91 | 15380.91 | 0 | 15380.91 | 100% | 0 |  | YES
| Kotulak, Donald | Tile | Garry | Garry | Completed | Yes | 33374.19 | 33374.19 | 0 | 33374.19 | 100% | 0 |  | YES
| Mark Dobson | SPF | EJ | EJ | Completed | Yes | 13035 | 13035 | 0 | 13035 | 100% | 0 |  | YES
| Tom Gallagher | Recoat | Gary | Gary | Completed | Yes | 10824.25 | 10824.25 | 0 | 10824.25 | 100% | 0 |  | YES
| Country Side Condo | SPF | Gary | Gary | Completed | Yes | 40000 | 40000 | 0 | 40000 | 100% | 0 |  | NO
| Antonio Sangineto | Shingle | AJ | Shawn | Completed | Yes | 17781 | 17781 | 0 | 17781 | 100% | 0 |  | NO |  | Regal Trace Ltd 540 NW 4th Ave Fort Lauderdale, FL 33111 954-468-1800
| Milton & Barbara Jones Const. - 18 NW | Shingle | Lewis | Lewis | Completed | Yes | 17479 | 17479 | 0 | 17479 | 100% | 0 |  | YES
| Milton & Barbara Jones Const. - 22 NW | Shingle | Lewis | Lewis | Completed | Yes | 17479 | 17479 | 0 | 17479 | 100% | 0 |  | NO | STATUS LEGEND: | Amkin Mgmt-Bainbridge 1501 Colquitt Bainbridge, GA
| Gary Williams | Tile/SPF Flat | Dave | Scott | Completed | Yes | 37393 | 37393 | 12679.38 | 24713.62 | 100% | 0 |  | NO | In Process | Amkin Mgmt-Flamingo Seafood 2798 E Atlantic Blvd. Pompano Beach, FL 32062
| Ken Marone 7810 NW 73 Avenue, Tamarac, Fl 33321 | SPF | Shawn | Garry | Completed | Yes | 13650 | 14877.51 | 0 | 14877.51 | 109% | -1227.51 |  | NO | POSTPONED | Amkin Mgmt-Westbay 311 W Bay Street Jacksonville, FL 32202
[10 empty] | 0 | #DIV/0! | 0 |  |  |  | Meadowbrook Tower L 319 NE 14 Avenue Hallandale, FL 33009 416-453-7996
[10 empty] | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | #DIV/0! | 0 |  |  |  | Donnil Kenney 3095 S Military Trail Lake Worth, FL 33463 561-644-0077
[10 empty] | 0 | #DIV/0! | 0
[10 empty] | 0 | #DIV/0! | 0 |  |  |  | The Field - British Oak 3281 Griffin Road Fort Lauderdale, Florida 33312 954-649-6082 Marie McMullen
[10 empty] | 0 | #DIV/0! | 0 |  |  |  | Regency Island Dunes 8640/8650 S Ocean Dr Jensen Beach, FL 34957
[7 empty] | 1601686.58 | 1452521.81 | 1720 | 1346178.46 |  | 149164.77
| Residential Projects | Project Count | Contract Amount | Gross Amnt TD Invoiced | Outstanding Invoice Amnt | Gross Amnt Paid | Contract Amnt Not Invoiced
| Projects In Process: | 8 | 267672.83 | 145082.72 | 38053.59 | 107029.13 | 122590.11
| Projects Delayed: | 1 | 10085 | 0 | 0 | 0 | 10085
| Projects In Pending: | 4 | 39134.15 | 23210.92 | 1720 | 21490.92 | 15923.23
| Projects with No Contract: | 0 | 0 | 0 | 0 | 0 | 0
| Projects In Litigation: | 0 | 0 | 0 | 0 | 0 | 0
| Sub-Total: | 13 | 316891.98 | 168293.64 | 39773.59 | 128520.05 | 148598.34
| Projects In Completed: | 48 | 1284794.6 | 1284228.17 | 66569.76 | 1217658.41 | 566.43
| Grand Total: | 61 | 1601686.58 | 1452521.81 | 106343.35 | 1346178.46 | 149164.77

## Repairs
Repairs
| Date: | 2026-02-05
Active Repair Projects
| Repairs Info. |  |  |  |  | Repair Status |  | Repairs Bookkeeping | [5 empty] | Comments | NTO
[8 empty] | Gross Amnt Invoiced: | 12000 | <-Active Projects Amnts-> |  | Gross Outstanding Invoiced Amnt: | 4625
| Job Name | Type of Work | Category | Supervisor | Salesperson | Project Status | Contract Signed | Contract Amount | Gross Amnt TD Invoiced | Outstanding Invoice Amnt | Gross Amnt Paid | % of Contract Invoiced | Contract Amnt Not Invoiced |  |  |  | Project Status
| Courtyard Marriott Hotel Coral springs 620 n University Dr | Repair | Repairs | Gabriella | Scott | Completed | Yes | 11000 | 11000 | 11000 | 5500 | 100% | 0 | completed 1/23/26 50% paid awaiting on Noor to inform terry when check can be picked up this week
| MAX CHANG 934 Bluewood Terrace, Weston, FL 33327 | Repair Roof Leak | Repairs | Gabriella | Santiago | Completed | Yes | 1712.25 | 1712.25 | 0 | 1712.25 | 100% | 0 | paid in full
| MAX CHANG 934 Bluewood Terrace, Weston, FL 33327 | Repair Roof Leak | Repairs | Gabriella | Santiago | Completed | Yes | 950 | 950 | 0 | 950 | 100% | 0 | Paid in full 10/27/25
| Chateau at Boca Grove 7383 Orangewood lane Boca Raton, FL 33433 | Repair Roof Leak | Repairs | Gabriella | Garry | Completed | yes | 1200 | 1200 | 0 | 1200 | 100% | 0 | paid in full 10/3/25
| Chateau at Boca Grove 7383 Orangewood lane Boca Raton, FL 33433 | Repair Roof Leak | Repairs | Gabriella | Garry | Completed | Yes | 5300 | 5300 | 0 | 5300 | 100% | 0 | paid in full 11/5/25
| Amelia Guerra 1250 NE 125th Street North Miami, Fl 33161 | Repair Roof Leak | Repairs | Gabriella | Santiago | Completed | Yes | 6800 | 6800 | 0 | 6800 | 100% | 0 | paid in full 10/31/25
| Skymark Real Estate Office 1540 s federal hwy pompano beach fl 33062 | Repair Roof Leak | Repairs | Garry | Garry | Completed | yes | 1500 | 1500 | 0 | 1500 | 100% | 0 | completed 11/3/25 invoice 43823 paid in full 11/18/25
| Ryan Patch 2172 Queen Palm Road Boca Raton, Fl 33432 | Repair Roof Leak | Repairs | Gabriella | Santiago | Completed | Yes | 1200 | 1200 | 0 | 1200 | 100% | 0 | paid in full 10/3/25
| Starlight Towers 6000 N Ocean Blvd. Lauderdale-by-the-sea, Fl 33308 | Repair | Repairs | Garry | Garry | Completed | Yes | 5310 | 0 | 0 | 0 | 0% | 5310 | PAID IN FULL AS OF 11/4/25
| Starlight Towers 6000 N Ocean Blvd. Lauderdale-by-the-sea, Fl 33308 | REPAIR | Repairs | Garry | GARRY | Completed | YES | 2360 | 2360 | 0 | 2360 | 100% | 0 | WORK COMPLETED 11/4/25 INV 43822 PAYMENT date 11/21/25
| MARKETPLACE BSO OFFICE2926 N ST RD 7 OAKLAND PARK | Repair Roof Leak | Repairs | Gabriella | Garry | Completed | YES | 2500 | 0 | 0 | 2500 | 100% | 2500 | completed 12/22/25 awaiting payment
| Sam Levine 6644 Patio LN | repair | Repairs | Gabriella | Garry | Completed | Yes | 2334 | 2334 | 0 | 2334 | 100% | 0 | paid in full
| Casablanca Isles Boynton beach | Repair | Repairs | Gabriella | Gabriella | Completed | Yes | 1895 | 1895 | 0 | 1895 | 100% | 0 | PAID IN FULL 10/21/25
| JCI-2460 PGA Blvd. |  |  | EJ | Garry | Litigation | No | 12000 | 12000 | 0 | 12000 | 100% | 0 | Under Litigation | YES
| Meadowbrook L 319 NE 14 Ave Hallandale Beach 33009 | Repair | Repairs | Gabriella | Garry | Completed | No Contract | 250 | 250 | 250 | 0 | 100% | 0 | service charge, no roof leaks - Meadowbrook will not pay invoice
| Embassy Park Condo 1700 Embassy Dr WPB | Repair | Repairs | Garry | Garry | Completed | No Contract | 250 | 250 | 0 | 250 | 100% | 0 | PAID IN FULL 9/29/25
| Variety Foods 1300 SW 2nd St | Repair Roof Leak | Repairs | garry | garry | Completed | Yes | 3595 | 3595 | 0 | 3595 | 100% | 0 | paidin full 9/23/25
| Nationwide loan consultants | repair Roof Leak | Repairs | Garry | Garry | Completed | Yes | 2900 | 2900 | 0 | 2900 | 100% | 0 | paid in full 9/11/25
| Galt Ocean Terrace | Repair/change order | Repairs | Garry | Scott | Completed | Yes | 16747.5 | 16747.5 | 0 | 16747.5 | 100% | 0 | PAID IN FULL PLUS 1100 EXTRA WORK CHARGE
| Xavier Doe 1210 Van Buren Street, Hollywood, Fl 33019 | Repair | Repairs | Gabriella | Santiago | Completed | Yes | 1000 | 1000 | 0 | 1000 | 100% | 0 | PAID IN FULL 8/14/25
| Yvette & Shaun 9146 Pinto Dr Wellignton | Repair Roof Leak | Repairs | Gabriella | Gabriella | Completed | Yes | 2200 | 2200 | 0 | 2200 | 100% | 0 | PAID IN FULL 8/22/25
| Geneva Group Jennafer Belabin 1015 North State Road 7, Royal Palm Beach, fl 33411 | Repair | Repairs | Gabriella | Santiago | Completed | Yes | 1645.15 | 1645.15 | 0 | 1645.15 | 100% | 0 | PAID IN FULL
| Jill Moss 1 Seneca Rd, Sea Ranch Lakes | Main./Repair | Repairs | Santiago | Santiago | Completed | Yes | 2456.37 | 2456.37 | 0 | 2456.37 | 100% | 0 | PAID IN FULL 7/22/25
| Krystina Wright - Prestigious Property Management 2405 Lake Drive, Riviera Beach, Fl 33404 | Repair | Repairs | Gabriella | Santiago | Completed | Yes | 2168.35 | 2168.35 | 0 | 2168.35 | 100% | 0 | PAID IN FULL 7/18/25
| Rick Howard Havana Dr Boca Ration | Repair | Repairs | Garry | Garry | Completed | Yes | 900 | 900 | 0 | 900 | 100% | 0 | PAID IN FULL
| Rick Howard Havana Dr Boca Ration | Repair | Repairs | Garry | Garry | Completed | Yes | 2972 | 2972 | 0 | 2972 | 100% | 0 | PAID IN FULL
| Chateau Gardens Condo 311 Liberty St Hollywood | Main./Repair | Repairs | Gabriella | Garry | Completed | Yes | 3500 | 3500 | 0 | 3500 | 100% | 0 | PAID IN FULL 7/21/25
| Raymond Ortiz c/o Keven Kane 3954 NW 63rd Terrace Coral Springs, Fl 33067 | Tile | Repairs | Shawn | Santiago | Completed | Yes | 900 | 900 | 0 | 900 | 100% | 0 | PAID IN FULL 6/12/25
| Galt Ocean Terrace | Main./Repair | Repairs | Garry | Scott | Completed | Yes | 19168 | 19168 | 0 | 19168 | 100% | 0 | PAID IN FULL
| Regent Park Condo 1900 Van Buren Street Hollywood, Fl 33020 | Foam | Repairs | Scott | Scott | Completed | Yes | 34125 | 34125 | 0 | 34125 | 100% | 0 | PAID IN FULL |  | Pressure Clean
| Regent Park Condo 1900 Van Buren Street Hollywood, Fl 33020 | Foam | Repairs | Scott | Scott | Completed | Yes | 58000 | 58000 | 0 | 58000 | 100% | 0 | job completed 6.10.25 paid in full |  | Repairs
| Regent Park Condo 1900 Van Buren Street Hollywood, Fl 33020 | Foam | Repairs | Scott | Scott | Completed | Yes | 6500 | 6500 | 0 | 6500 | 100% | 0 | PAID IN FULL |  | Warranty
| Casablanca Isles Boynton beach | 3 roof repairs | Repairs | Shawn | Santiago | Completed | Yes | 5925.3 | 5925.3 | 0 | 5925.3 | 100% | 0 | completed and paid
| Onclave Boca Dunes 10214 Akenside Drive Boca Raton, Fl 33428 | Tile repairs | Repairs | Shawn | Santiago | Completed | Yes | 1085.3 | 1085.3 | 0 | 1085.3 | 100% | 0 | completed and paid
| Gerald Legow - 4 | Repair Roof Leak | Repairs | Gary | Gary | Completed | Yes | 250 | 0 | 0 | 0 | 0% | 250 | PAID IN FULL
| Bob Porter | SPF over Flat Roof | Repairs | Garry | Garry | Completed | Yes | 4150 | 4150 | 0 | 4150 | 100% | 0 | PAID IN FULL
| Casablanca Isles | Tile Replacement | Repairs | Shawn | Santiago | Completed | Yes | 5632.45 | 5632.45 | 0 | 5632.45 | 100% | 0
| HASIB MOHAMMED | Roof Repair | Repairs | Santiago | Gabriella | Completed | Yes | 2950 | 2950 | 0 | 2950 | 100% | 0
| ROBERT MORIN MORSE LIFE | Roof Repair | Repairs | Gabriella | Gabriella | Completed | Yes | 2650 | 2650 | 0 | 2650 | 100% | 0 | PAID IN FULL
| ROBERT MORIN MORSE LIFE | Roof Repair | Repairs | Gabriella | Gabriella | Completed | yes | 6875 | 6875 | 0 | 6875 | 100% | 0 | PAID IN FULL
| Allsteel & Gypsum Products 1250 NW 23rd Avenue Ft. Lauderdale, Fl | Roof Repair | Repairs | Garry | Garry | Completed | Yes | 2400 | 2400 | 0 | 2400 | 100% | 0 | PAID IN FULL
| Fliori Financial Group | Leak Repair | Repairs | EJ | EJ | Completed | Yes | 3100 | 3100 | 0 | 3100 | 100% | 0
| Leroy McKenzie | Tile Replacement | Warranty | EJ | EJ | Completed | Yes | 750 | 750 | 0 | 750 | 100% | 0 |  |  |  | Pending
| Midtown Manor |  |  | EJ | EJ | Completed | Yes | 4750 | 2375 | 2375 | 0 | 50% | 2375 | Inv no 43048 - Final Payment | YES |  | Delayed
| Midtown Manor |  |  | EJ | EJ | Completed | Yes | 1650 | 1650 | 1650 | 0 | 100% | 0 | Inv no 42047 | NO |  | Litigation
| Palm Aire Condo 6-Campbell-3655 | Repair |  | EJ | EJ | Completed | Yes | 350 | 350 | 350 | 0 | 100% | 0 | Inv no 43202 - Service Call - Water Test |  |  | Pending
| Palm Aire Condo 6-Campbell-3655 | Repair |  | EJ | EJ | Completed | Yes | 1250 | 1250 | 0 | 1250 | 100% | 0 |  | YES |  | Completed
| Palm Aire Condo 6-Campbell-3655 | Repair |  | EJ | EJ | Completed | Yes | 1250 | 1250 | 0 | 1250 | 100% | 0 |  | NO |  | In Process | Greensward Village 745 Greenward Ct. Delray Beach, FL 33069 954-984-1000
| Panda Catering | Foam | Repairs | EJ | EJ | Completed | Yes | 4000 | 4000 | 0 | 4000 | 100% | 0 |  | YES |  | No Contract | Isles of Boca Association 23229 Fountain View Drive Boca Raton, Fl 33433
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[11 empty] | 0 | #DIV/0! | 0
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | NO
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | NO |  |  | Regal Trace Ltd 540 NW 4th Ave Fort Lauderdale, FL 33111 954-468-1800
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | NO |  | STATUS LEGEND: | Amkin Mgmt-Bainbridge 1501 Colquitt Bainbridge, GA
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | NO |  | In Process | Amkin Mgmt-Flamingo Seafood 2798 E Atlantic Blvd. Pompano Beach, FL 32062
[11 empty] | 0 | #DIV/0! | 0 |  | NO |  | POSTPONED | Amkin Mgmt-Westbay 311 W Bay Street Jacksonville, FL 32202
[11 empty] | 0 | #DIV/0! | 0 |  |  |  |  | Meadowbrook Tower L 319 NE 14 Avenue Hallandale, FL 33009 416-453-7996
[11 empty] | 0 | #DIV/0! | 0 |  | YES
[11 empty] | 0 | #DIV/0! | 0 |  |  |  |  | Donnil Kenney 3095 S Military Trail Lake Worth, FL 33463 561-644-0077
[11 empty] | 0 | #DIV/0! | 0
[11 empty] | 0 | #DIV/0! | 0 |  |  |  |  | The Field - British Oak 3281 Griffin Road Fort Lauderdale, Florida 33312 954-649-6082 Marie McMullen
[11 empty] | 0 | #DIV/0! | 0 |  |  |  |  | Regency Island Dunes 8640/8650 S Ocean Dr Jensen Beach, FL 34957
[8 empty] | 253356.67 | 242921.67 | 4625 | 240796.67 |  | 10435
| Residential Projects | Project Count | Contract Amount | Gross Amnt TD Invoiced | Outstanding Invoice Amnt | Gross Amnt Paid | Contract Amnt Not Invoiced
| Projects In Process: | 0 | 0 | 0 | 0 | 0 | 0
| Projects Delayed: | 0 | 0 | 0 | 0 | 0 | 0
| Projects In Pending: | 0 | 0 | 0 | 0 | 0 | 0
| Projects with No Contract: | 0 | 0 | 0 | 0 | 0 | 0
| Projects In Litigation: | 1 | 12000 | 12000 | 0 | 12000 | 0
| Sub-Total: | 1 | 12000 | 12000 | 0 | 12000 | 0
| Projects In Completed: | 47 | 241356.67 | 230921.67 | 4625 | 228796.67 | 10435
| Grand Total: | 48 | 253356.67 | 242921.67 | 4625 | 240796.67 | 10435

## Maintenance
Maintenance
| Date: | 2026-02-05
Active Maintenance Projects
| Maintenance Info. |  |  |  |  | Maint. Status |  | Maintenance Bookkeeping | [5 empty] | Comments | NTO
[8 empty] | Gross Amnt Invoiced: | 0 | <-Active Projects Amnts-> |  | Gross Outstanding Invoiced Amnt: | 42995.5
| Job Name | Type of Work | Category | Supervisor | Salesperson | Project Status | Contract Signed | Contract Amount | Gross Amnt TD Invoiced | Outstanding Invoice Amnt | Gross Amnt Paid | % of Contract Invoiced | Contract Amnt Not Invoiced |  |  |  | Project Status
| Cheryl Newton | Pressue Clean | Pressure Clean | Gabriella | Gabriella | Completed | Yes | 450 | 450 | 0 | 450 | 100% | 0 | PAID IN FULL | YES
| Kim Cronin | Maintenance | Warranty | Garry | Garry | Completed | Yes | 1200 | 1200 | 0 | 1200 | 100% | 0 | PAID IN FULL
| Aisha Eckroth | Maintenance | Gabriella | Gabriella | Santiago | Completed | Yes | 950 | 950 | 550 | 400 | 100% | 0 | financing 200$ per Santiagio contract terms
| Peggy Salomone | Pressure Wash/Recoat | Warranty | Garry | Garry | Completed | yes | 3000 | 3000 | 0 | 3000 | 100% | 0 | PAID IN FULL
| Tradewinds Condo Assn | Maintenance | Warranty | Gabriella | Gabriella | Completed | Yes | 6000 | 6000 | 0 | 6000 | 100% | 0 | PAID IN FULL
| Marseilles Court at the Fountains | Maintenance | Warranty | Gabriella | Gabriella | Completed | Yes | 13104 | 13104 | 0 | 13104 | 100% | 0 | PAID IN FULL
| Tom Jeffers | Maintenance | Pressure Clean | Garry | Garry | Completed | Yes | 3900 | 3900 | 0 | 3900 | 100% | 0 | PAID IN FULL
| Robert & Rose (Luke Residence) | Pressure Wash/Recoat | Warranty | Garry | Gabriella | Completed | Yes | 5100 | 5100 | 0 | 5100 | 100% | 0 | PAID IN FULL 8/12/25
| Starlight Towers | Maintenance | Pressure Clean | Garry | Garry | Completed | Yes | 6510 | 6510 | 0 | 6510 | 100% | 0 | PAID IN FULL 8/13/25
| ANTHONY RAWSON | Maintenance |  | Garry | Garry | Completed | YES | 4600 | 4600 | 0 | 4600 | 100% | 0 | Need to pick up check
| Seagate @ Gulfstream | Maintenance | Warranty | Gabriella | Gabriella | Completed | Yes | 3500 | 3500 | 0 | 3500 | 100% | 0 | Inv no 43560 - Roof Maintenance
| Perry Klimas | Pressure Wash | Warranty | Gabriella | Gabriella | Completed | Yes | 450 | 450 | 0 | 450 | 100% | 0 | Inv no 43597 - Gen. Roof cleaning
| Parkview Point Condos | Maintenance | Warranty | Garry | Garry | Completed | Yes | 4600 | 0 | 0 | 0 | 0% | 4600 | paid in full 9/19/25
| Berger Commercial Realty JMA Investment 2075-2197 North Powerline Rd. Pompano Beach, FL 33069 | Pressure wash |  | Gabriella | Scott | Completed | yes | 23691 | 23691 | 11845.5 | 11845.5 | 100% | 0 | 50% balance due awating check payment
| Berger Commercial Realty Marketplace plaza 3662-3704 West Oakland Park | pressue wash |  | Gabriella | Scott | Completed | Yes | 32000 | 16000 | 16000 | 0 | 100% | 16000 | pending completion
| Portabella Townhomes 780 Jeffery Street Boca Raton, FL 33487 | Maintenance | Pressure Clean | Garry | Garry | Completed | Yes | 5500 | 5500 | 0 | 5500 | 100% | 0 | paid in full 10/3/25
| Darlene & Jorge | Maintenance | Warranty | Gabriella | Santiago | Completed | yes | 18992.5 | 18992.5 | 0 | 18992.5 | 100% | 0 | PAID IN FULL 8/10/25
| Ed & Pamela 6341 NE 15 AVE FORT LAUDERDALE, FL 33334 | Pressure Wash/Recoat | Warranty | Garry | Gabriella | Completed | Yes | 8975 | 8975 | 0 | 8975 | 100% | 0 | paid in full 10/20/25
| Palm Aire Condo #6 (Patio Homes) | Maintenance | Warranty | Gabriella | Gabriella | Completed | Yes | 0 | 0 | 0 | 0 | 50% | 0 | invoiced 50% deposit payment pending 9/4/25 |  | Pressure Clean
| Palm Aire Condo #6 (Villas) | Maintenance | Warranty | Gabriella | Gabriella | Completed | yes | 3800 | 1600 | 0 | 1600 | 50% | 2200 | invoiced 50% deposit payment pending 9/4/25 |  | Repairs
| Palm Aire Condo #6 (Building 78A) | Maintenance | Warranty | Gabriella | Gabriella | Completed | yes | 3900 | 0 | 0 | 0 | 50% | 3900 | invoiced 50% deposit payment pending 9/4/25 |  | Warranty
| Palm Aire Condo #6 (Building 77) | Maintenance | Warranty | Gabriella | Gabriella | Completed | yes | 3900 | 0 | 0 | 0 | 50% | 3900 | invoiced 50% deposit payment pending 9/4/25
| Palm Aire Condo #6 (Building 76) | Maintenance | Warranty | Gabriella | Gabriella | Completed | yes | 3900 | 0 | 0 | 0 | 50% | 3900 | invoiced 50% deposit payment pending 9/4/25
| Palm Aire Condo #6 (Building 75) | Maintenance | Warranty | Gabriella | Gabriella | Completed | yes | 2900 | 0 | 0 | 0 | 50% | 2900 | invoiced 50% deposit payment pending 9/4/25
| Palm Aire Condo #6 (Building 74) | Maintenance | Warranty | Gabriella | Gabriella | Completed | yes | 2900 | 0 | 0 | 0 | 50% | 2900 | invoiced 50% deposit payment pending 9/4/25
| Palm Aire Condo #6 (Building 73) | Maintenance | Warranty | Gabriella | Gabriella | Completed | yes | 2900 | 0 | 0 | 0 | 50% | 2900 | invoiced 50% deposit payment pending 9/4/25
| Palm Aire Condo #6 (Building 72) | Maintenance | Warranty | Gabriella | Gabriella | Completed | yes | 3900 | 0 | 0 | 0 | 50% | 3900 | invoiced 50% deposit payment pending 9/4/25
| Palm Aire Condo #6 (Building 71) | Maintenance | Warranty | Gabriella | Gabriella | Completed | yes | 2900 | 0 | 0 | 0 | 50% | 2900 | invoiced 50% deposit payment pending 9/4/25
| Palm Aire Condo #6 (Building 70) | Maintenance | Warranty | Gabriella | Gabriella | Completed | yes | 3900 | 0 | 0 | 0 | 50% | 3900 | invoiced 50% deposit payment pending 9/4/25
| Cypress Creek Condos | Maintenance | Warranty | Gabriella | Scott | Completed | yes | 2950 | 0 | 0 | 0 | 0% | 2950 | project not started yet
| Coral Gables Granda | Maintenance | Warranty | Gabriella | Scott | Completed | yes | 5600 | 5600 | 5600 | 0 | 100% | 0 | awaiting payment
| Country Club Towers Coral Springs | Maintenance |  | Gabreilla | Scott | Completed | yes | 3600 | 3600 | 0 | 3600 | 100% | 0 | project not started yet
| Patricia Chichester 908 SW 6 Ave boynton beach | roof cleaning |  | Gabriella | Gabriella | Completed | yes | 475 | 475 | 0 | 475 | 100% | 0 | paid in full 9/19/25
| Patricia Chichester 908 SW 6 Ave boynton beach | Maintenance |  | Gabriella | Terry | Completed | Yes | 9000 | 9000 | 9000 | 9000 | 100% | 0 | contract signed 1/5/26 paid 50% deposit 50% balance paid with CC 1/29/26
[11 empty] | 0 | #DIV/0! | 0
[11 empty] | 0 | #DIV/0! | 0 |  | No
[11 empty] | 0 | #DIV/0! | 0 |  | NO |  | Pending
[11 empty] | 0 | #DIV/0! | 0 |  | Yes |  | Completed
[11 empty] | 0 | #DIV/0! | 0 |  | YES |  | Delayed
[11 empty] | 0 | #DIV/0! | 0 |  | NO |  | Litigation
[11 empty] | 0 | #DIV/0! | 0 |  | YES |  | Not Started
[11 empty] | 0 | #DIV/0! | 0 |  | NO |  | In Process
[11 empty] | 0 | #DIV/0! | 0 |  | YES |  | No Contract
[11 empty] | 0 | #DIV/0! | 0 |  | NO
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | NO
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | NO
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | YES
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | NO |  | STATUS LEGEND:
[10 empty] | 0 | 0 | #DIV/0! | 0 |  | NO |  | In Process
[11 empty] | 0 | #DIV/0! | 0 |  | NO |  | POSTPONED
[11 empty] | 0 | #DIV/0! | 0
[11 empty] | 0 | #DIV/0! | 0 |  | YES
[11 empty] | 0 | #DIV/0! | 0
[11 empty] | 0 | #DIV/0! | 0
[11 empty] | 0 | #DIV/0! | 0
[11 empty] | 0 | #DIV/0! | 0
[8 empty] | 199047.5 | 142197.5 | 42995.5 | 108202 |  | 56850
| Residential Projects | Project Count | Contract Amount | Gross Amnt TD Invoiced | Outstanding Invoice Amnt | Gross Amnt Paid | Contract Amnt Not Invoiced
| Projects In Process: | 0 | 0 | 0 | 0 | 0 | 0
| Projects Delayed: | 0 | 0 | 0 | 0 | 0 | 0
| Projects In Pending: | 0 | 0 | 0 | 0 | 0 | 0
| Projects with No Contract: | 0 | 0 | 0 | 0 | 0 | 0
| Projects In Litigation: | 0 | 0 | 0 | 0 | 0 | 0
| Sub-Total: | 0 | 0 | 0 | 0 | 0 | 0
| Projects In Completed: | 34 | 199047.5 | 142197.5 | 42995.5 | 108202 | 56850
| Grand Total: | 34 | 199047.5 | 142197.5 | 42995.5 | 108202 | 56850